## VoIP
Sl.No | Task Description | Description | Task Owner | Start Date | Enddate | Status | Remarks
1 | GiTLab backup | • Back up the exiting server • Store it in back up folder | Kannan/Vinoth | 2018-06-04 | 2018-06-04
2 | GitLab Server Creation | • Create CentOS with 2GB Ram, 2 CPU, 20GBHDD • Root and admin account | Kannan | 2018-06-04 | 2018-06-04
3 | GitLab Installation and setup | • Download Latest GITLab • Install the backup installer. • Validate the structure • Create new repo and do all test (Branching, merging, cloning etc) | Kannan/Vinoth | 2018-06-04 | 2018-06-05
4 | Application server Creation | • Create Ubuntu 16.04.1, 64-bit Linux (Linux version 4.9.15-x86_64)CentOS with 2GB Ram, 2 CPU, 20GBHDD • Root and admin account | Vinoth | 2018-06-06 | 2018-06-06
5 | Install application dependent software | • Database: MySQL Version 14.14, Distribution 5.7.18 • Programing Language: PHP 7.1.7-1 • Framework: Laravel 5.5.x • HTTP Server: Apache httpd 2.4 • Output data Character code: Shift-JIS • API data format: JSON • Authentication Mechanism: oAuth 2.0 | Vinoth/Kannan | 2018-06-06 | 2018-06-07
6 | Jenkins Installation and setup | • Create CentOS with 2GB Ram, 2 CPU, 20GBHDD • Root and admin account creation | RajaGanapathy | 2018-06-06 | 2018-06-07
7 | Job configuration and testing | • Create VoIP job • Do checkout and deploy to destination server | RajaGanapathy | 2018-06-06 | 2018-06-07
8 | Ansible learning with workshop | • Installation and environmenr setup • Yaml basics • Ansible Commands • Ansible Playbooks • Ansible Roles and Variables • Exercises | Vinoth/RajaGanapathy | 2018-06-06 | 2018-06-12
9 | Ansible on VoIP using Jenkins | Implement to VoIP | Vinoth/RajaGanapathy/Kannan | 2018-06-13 | 2018-06-15
10 | Docker learning with workshops | • Installation and configuration • Docker Images • Docker Files • Docker Repositories • Docker CI • Exercise | Vinoth/RajaGanapathy | 2018-06-18 | 2018-06-26
11 | Docker on VoIP | Implement to VoIP | Vinoth/RajaGanapathy/Kannan | 2018-06-27 | 2018-06-30

## WebArena
Sl.No | Task Description | Description | Task Owner | Start Date | Enddate | Status | Remarks

## SkillMatrix
Sl.No | Task Description | Description | Task Owner | Start Date | Enddate | Status | Remarks