## Slide 1: NTTPC Phase2 Development Plan
May 2018
May 2018 (Version <1.0>)

## Slide 2: Agenda
Requirements
Development Plan
Team Chart
Development Tools
Deliverables
Efforts
Assumptions & Dependencies

## Slide 3: Requirements
Sprint | Sprint Duration | Major items | Minor items | Sub items | Development Complexity | Remarks
Sprint 1 | 2 Weeks | API | API Re- construction | Modify User Authentication | High | 
 |  |  |  | Remove super admin privileges | Medium | 
 |  | Input from NTT Com | Automating the flow | Automate NTT Com file acquisition | High | 
 |  |  |  | Decrypting and extracting the files | High | 
Sprint 2 | 2 Weeks | VoIP |  | Providing the extracted files as Input to the Tool | Medium | 
 |  |  |  | Initiating the Tool after providing Input | Medium | 
Sprint 3 | 1 Month |  | Tool Execution | VOIP Tool Development | High | Parallel Activities
 |  |  |  | Generating Output files and Updating Database | High | 
 |  |  |  | Archive/delete data after storage period is exceeded | High | 
Sprint 3.1 | 1 Month | Web GUI | Admin and User Screen | Admin Panel, User Panel and Authentication Screens | High | 
 |  |  | Upload and Download | GUI for Uploading and Downloading | Medium | 
 |  |  | Configuration Screen | GUI for Application Configuration | Medium | 
Sprint 4 | 2 Weeks | User Management | User Authentication | Authenticate using mail address and password | Medium | 
 |  |  |  | Password initialization function | Medium | 
 |  |  | User CRUD | Admin user CRUDS for Admin user | High | 
 |  |  |  | OEM user CRUDS for Admin user | High | 
Sprint 5 | 2 Weeks |  |  | Self update for OEM user | Medium | 
 |  |  |  | ISP CRUD Operation | Medium | 
 |  |  |  | GIP Operations | Medium | 
 |  |  |  | File information (View count, Final view date, uploaded by) | Medium | 
 |  |  |  | Application Configurations/Settings | Medium | 
Sprint 6 | 2 Weeks | File Download, Upload and Removal | File download | Month wise file list search | Medium | 
 |  |  |  | Download selected files | Low | 
 |  |  | File upload | File upload related to OEM user | Medium | 
 |  |  |  | upload cancellation | Medium | 
Sprint 7 | 2 Weeks | Notification | Notification function | Automatic mail notification function after certain period of time is elapsed since the upload was completed. | Medium | 
 |  |  |  | Automatic notification on/off selection | Low | 
 |  |  |  | Cancel transmission while cancelling upload | Medium | 
Notes: Our Fast Facts:
Incorporated in 1997
Operations in 11 countries
Among IAOP’s “Global Outsourcing 100” for seven consecutive years
Solution Verticals: Banking & Finance, Education, Government, Social Services, Hospitality, Healthcare
An NTT Communications company since 2010
Delivery Centre in Singapore, Malaysia, Indonesia, India, Philippines and Thailand
ISO 9001:2008 certified
Large Stack of IT Services offered horizontally across all verticals
Over 2,200 employees
Employees from 23 nationalities
Client relationship lasting over 18 years
In-country and right-shored teams of domain and industry experts

## Slide 4: Development Plan
NTTPC Phase2 Development schedule
Development Method - AGILE
Development Period - 4 Months (Weekly Sprint)
Task
Schedule
Requirement clarification
Sprint1
W0
Sprint3 & 3.1
UAT Release
D3 D4
D5 ~ D8
D9 D10
Task
Schedule
Check development back-log and create requirements
Design
D1 D2
D11 D12
Dev and testing
Create UAT deployment procedure
MTG
MTG
UAT Release
Overall schedule
Each sprint’s
schedule
W1
W2
W3
W4
W5
W6
W7
W8
Sprint2
UAT Release
UAT Release
UAT Release
Task
Schedule
Sprint4
W9
UAT Release
W10
W11
W12
W13
W14
W15
W16
W17
Sprint5
UAT Release
UAT Release
UAT Release
Sprint6
Sprint7
Week1
Week1
UAT Release
Month1
Month2
Month3
Month4
W - Week
D - Day

## Slide 5: Team Chart
Project Manager
(1)
Quality Analyst
(2)
Senior Developer(PHP)
(1)
Developer(PHP)
(1)
UI/UX Developer
(1)
Business Analyst
(1)
DevOps
(1)
Bilingual Coordinator (1)

## Slide 6: Roles & Responsibilities
# | Role | Responsibility
1 | Project Manager | Responsible for overall direction, management and guidance to entire project Develop project plan, identify milestones and manage project deliverables Manage communications and resolve issues
2 | Business Analyst | Requirements gathering & Analysis Prepare requirement specification document Single Point of Contact for all business requirements Ensure all related documents are prepared
3 | DevOps | Responsible to setup the environment and DevOps tools. Responsible for release management.
4 | Sr. PHP Developer (Project Lead) | Responsible for architect and design of the entire project Prepare design specification document Perform the code review Develop the complex modules
5 | PHP Developer | Development of modules Perform unit testing Resolve program issues
6 | UI Developer | Development of UI & Mobile responsiveness Provide support on AngularJS Perform unit testing Resolve UI issues
7 | QA | Prepare SIT test cases Perform SIT testing Perform Regression testing Ensure the quality standards are maintained Ensure documentation of testing is maintained

## Slide 7: Development Tools
Project Management
  Redmine
Communication
  Slack
Source code management
  GitHub/GitLab/Bitbucket
Automation Testing
  Selenium
Configuration management
  Ansible
Auto Deploy
  Jenkins

## Slide 8: Deliverables
# | Deliverables - For every Sprint
1 | Wireframes of requirements
2 | SIT test cases & results
*Deliverables in Japanese
Japanese user manual will be delivered after 1 week of project completion.
# | Deliverables - After all sprints
1 | Design document
2 | User manual *

## Slide 9: Assumptions & Dependencies
Delay in requirements confirmation may impact the sprint delivery and overall project delivery

## Slide 10
Emerio GlobeSoft Pte. Ltd. (HQ) Emerio House, 50 Ubi Crescent #01-05 Ubi Tech Park, Singapore 408568 Tel: +65 6349 2999 Fax: +65 6349 2966