## Index
Document Name |  |  | NTTPC Phase2 Development WBS v[Version Number]
Purpose |  |  | To track all activity's of NTTPC Phase 2 analysis
Created By /Date |  |  | Ganesh R /04-06-2018
Maintained By |  |  | Ganesh R
Modification Details
# | Version | Modified Date | Sheet Name | Section Modified | Modification Details
1 | 1.0 | 2018-06-04 | All Sheets | 1st Version Created | All
1 | 2.0 | 2018-06-21 | WBS | WBS schedule | WBS schedule updated based on the SOW

## WBS
Task Name | % Complete | Start | Finish | Predecessors | Resource Names | Remarks
NTTPC VOIP Phase 2 Development | 0% | Fri 22-06-18 | Fri 12-10-18
Kick-off Meeting | 0% | Wed 06-06-18 | Thu 07-06-18
Project Communication | 0% | Fri 22-06-18 | Fri 12-10-18
Weekly status meeting | 0% | Fri 22-06-18 | Fri 12-10-18
Ad-Hoc Meetings | 0% | Fri 22-06-18 | Fri 12-10-18
Weekly status report - Prepare & Publish | 0% | Fri 22-06-18 | Fri 12-10-18
Environment setup | 0% | Fri 22-06-18 | Thu 05-07-18
Preparation of development environment and data setup | 0% | Fri 22-06-18 | Mon 25-06-18 |  | DevOps
Construction of Development and QA environment | 0% | Mon 25-06-18 | Thu 28-06-18 | 8 | DevOps
CI Tools implementation and testing | 0% | Thu 28-06-18 | Tue 03-07-18 | 9 | DevOps
Environment setup review | 0% | Tue 03-07-18 | Thu 05-07-18 | 10 | PM
Sprint #1 (Dev, UT, SIT) | 0% | Fri 22-06-18 | Fri 06-07-18
Requirement Clarification & Documentation | 0% | Fri 22-06-18 | Fri 29-06-18
API Reconstruction-Modify User Authentication with email features | 0% | Fri 22-06-18 | Mon 25-06-18 |  | BA
API Reconstruction-Remove Super Admin Privileges | 0% | Mon 25-06-18 | Tue 26-06-18 | 14 | BA
Requirement specification document preparation | 0% | Tue 26-06-18 | Thu 28-06-18 | 15 | BA
High level design document preparation | 0% | Thu 28-06-18 | Fri 29-06-18 | 16 | BA
Development | 0% | Mon 25-06-18 | Fri 06-07-18
Coding & Unit Testing | 0% | Mon 25-06-18 | Thu 05-07-18
API Reconstruction-Modify User Authentication with email features | 0% | Mon 25-06-18 | Mon 02-07-18 | 14 | Developer 1
API Reconstruction-Remove Super Admin Privileges | 0% | Tue 26-06-18 | Thu 28-06-18 | 15 | Developers 2
Common/Helper Functions-Common functions creation & Framework creation | 0% | Thu 28-06-18 | Thu 05-07-18 | 21 | Developers 2
Code Review | 0% | Thu 05-07-18 | Fri 06-07-18
Code review and improvements | 0% | Thu 05-07-18 | Fri 06-07-18 | 22 | Developer 1,Developers 2
SIT Testing | 0% | Thu 28-06-18 | Thu 05-07-18
API Reconstruction-Modify User Authentication | 0% | Mon 02-07-18 | Thu 05-07-18 | 20 | QA 1
API Reconstruction-Remove Super Admin Privileges | 0% | Thu 28-06-18 | Tue 03-07-18 | 21 | QA2
Peer Review | 0% | Thu 28-06-18 | Thu 05-07-18
Peer Review & Improvements | 0% | Thu 28-06-18 | Thu 05-07-18 |  | PM
Sprint #1 - UAT | 0% | Thu 05-07-18 | Thu 12-07-18
UAT Testing and Feedback | 0% | Thu 05-07-18 | Thu 12-07-18 | 29 | Client
Sprint #2 (Dev, UT, SIT) | 0% | Fri 06-07-18 | Fri 03-08-18 | 29
Requirement Clarification & Documentation | 0% | Fri 29-06-18 | Thu 19-07-18
VoIP Calculation Tool Clarifications | 0% | Fri 29-06-18 | Thu 05-07-18 | 17 | BA
Requirement specification document preparation | 0% | Thu 05-07-18 | Thu 12-07-18 | 34 | BA
High level design document preparation | 0% | Thu 12-07-18 | Thu 19-07-18 | 35 | BA
Development | 0% | Fri 06-07-18 | Fri 03-08-18
Coding & Unit Testing | 0% | Fri 06-07-18 | Fri 27-07-18
VoIP Calculation Tool-Creating Directories, Database and Tables | 0% | Fri 06-07-18 | Tue 10-07-18 |  | Developer 1
VoIP Calculation Tool-Reading Data from the Input | 0% | Fri 06-07-18 | Wed 11-07-18 |  | Developers 2
VoIP Calculation Tool-General Functions and Validations | 0% | Tue 10-07-18 | Fri 13-07-18 | 39 | Developer 1
VoIP Calculation Tool-Base Charge Calculation | 0% | Wed 11-07-18 | Fri 13-07-18 | 40 | Developers 2
VoIP Calculation Tool-Additional Charge Calculation | 0% | Fri 13-07-18 | Tue 17-07-18 | 41 | Developer 1
VoIP Calculation Tool-Supplementary Charge Calculation | 0% | Fri 13-07-18 | Tue 17-07-18 | 42 | Developers 2
VoIP Calculation Tool-Call Charge Calculation | 0% | Tue 17-07-18 | Fri 20-07-18 | 43 | Developer 1
VoIP Calculation Tool-Monthly Charge Calculation | 0% | Tue 17-07-18 | Fri 20-07-18 | 44 | Developers 2
VoIP Calculation Tool-Universal Charge Calculation | 0% | Fri 20-07-18 | Tue 24-07-18 | 45 | Developer 1
VoIP Calculation Tool-Registration Charges Calculation | 0% | Fri 20-07-18 | Tue 24-07-18 | 46 | Developers 2
VoIP Calculation Tool-Generating Output files and Updating Database | 0% | Tue 24-07-18 | Fri 27-07-18 | 47 | Developer 1
VoIP Calculation Tool-Archive/delete data after storage period is exceeded | 0% | Tue 24-07-18 | Fri 27-07-18 | 48 | Developers 2
Code Review | 0% | Fri 27-07-18 | Fri 03-08-18
Code review and improvements | 0% | Fri 27-07-18 | Fri 03-08-18 | 50
SIT Testing | 0% | Fri 27-07-18 | Fri 03-08-18
VOIP Calculation Tool Testing (All charges and Total ) | 0% | Fri 27-07-18 | Fri 03-08-18 | 50 | QA 1,QA2
Peer Review | 0% | Fri 20-07-18 | Fri 03-08-18
Peer Review & Improvements | 0% | Fri 20-07-18 | Fri 03-08-18
Sprint #2 - UAT | 0% | Fri 03-08-18 | Fri 10-08-18
UAT Testing and Feedback | 0% | Fri 03-08-18 | Fri 10-08-18 | 56
Sprint #3 (UI/UX Design) - Parallel Activity With Sprint 2 | 0% | Fri 06-07-18 | Tue 07-08-18 | 29
Requirement Study | 0% | Fri 06-07-18 | Wed 11-07-18
Requirement Study and Understanding | 0% | Fri 06-07-18 | Tue 10-07-18 | 29 | UI/UX
UI/UX Related clarification from client | 0% | Tue 10-07-18 | Wed 11-07-18 | 61 | UI/UX
UI/UX | 0% | Wed 11-07-18 | Fri 03-08-18 | 62
Create visual design | 0% | Wed 11-07-18 | Mon 23-07-18 | 62
Visual Design-User Login | 0% | Wed 11-07-18 | Thu 12-07-18 | 62 | UI/UX
Visual Design-User Profile | 0% | Thu 12-07-18 | Thu 12-07-18 | 65 | UI/UX
Visual Design-Admin User Management CRUD | 0% | Thu 12-07-18 | Fri 13-07-18 | 66 | UI/UX
Visual Design-OEM User Management CRUD | 0% | Fri 13-07-18 | Mon 16-07-18 | 67 | UI/UX
Visual Design-ISP Management CRUD | 0% | Mon 16-07-18 | Tue 17-07-18 | 68 | UI/UX
Visual Design-OEM listing | 0% | Tue 17-07-18 | Tue 17-07-18 | 69 | UI/UX
Visual Design-Application Configuration | 0% | Tue 17-07-18 | Wed 18-07-18 | 70 | UI/UX
Visual Design-Month wise file listing | 0% | Wed 18-07-18 | Thu 19-07-18 | 71 | UI/UX
Visual Design-File Upload and Download | 0% | Thu 19-07-18 | Fri 20-07-18 | 72 | UI/UX
Visual Design-Application Configuration | 0% | Fri 20-07-18 | Fri 20-07-18 | 73 | UI/UX
Visual Design-Tool Input upload | 0% | Fri 20-07-18 | Mon 23-07-18 | 74 | UI/UX
Client Review | 0% | Wed 11-07-18 | Mon 23-07-18
Client Review and Acceptance | 0% | Wed 11-07-18 | Mon 23-07-18 | 62 | Client
Create UI | 0% | Mon 23-07-18 | Thu 02-08-18
UI-User Login | 0% | Mon 23-07-18 | Tue 24-07-18 | 77 | UI/UX
UI-User Profile | 0% | Tue 24-07-18 | Wed 25-07-18 | 79 | UI/UX
UI-Admin User Management CRUD | 0% | Wed 25-07-18 | Thu 26-07-18 | 80 | UI/UX
UI-OEM User Management CRUD | 0% | Thu 26-07-18 | Thu 26-07-18 | 81 | UI/UX
UI-ISP Management CRUD | 0% | Thu 26-07-18 | Fri 27-07-18 | 82 | UI/UX
UI-OEM listing | 0% | Fri 27-07-18 | Fri 27-07-18 | 83 | UI/UX
UI-Application Configuration | 0% | Fri 27-07-18 | Mon 30-07-18 | 84 | UI/UX
UI-Month wise file listing | 0% | Mon 30-07-18 | Tue 31-07-18 | 85 | UI/UX
UI-File Upload and Download | 0% | Tue 31-07-18 | Wed 01-08-18 | 86 | UI/UX
UI-Application Configuration | 0% | Wed 01-08-18 | Wed 01-08-18 | 87 | UI/UX
UI-Tool Input upload | 0% | Wed 01-08-18 | Thu 02-08-18 | 88 | UI/UX
Code Review | 0% | Tue 31-07-18 | Fri 03-08-18
Code review and improvements | 0% | Tue 31-07-18 | Fri 03-08-18 | 86 | UI/UX Reviewer
UI Testing | 0% | Thu 02-08-18 | Tue 07-08-18
Browser compatibility and RWD testing | 0% | Thu 02-08-18 | Tue 07-08-18 | 89 | QA 3(UI/UX QA test)
Peer Review | 0% | Fri 27-07-18 | Tue 07-08-18
Peer Review & Improvements | 0% | Fri 27-07-18 | Tue 07-08-18 |  | PM
Sprint #4 (Dev, UT, SIT) | 0% | Fri 03-08-18 | Mon 20-08-18
Requirement Clarification & Documentation | 0% | Thu 19-07-18 | Mon 06-08-18
GUI-User Management-Authenticate using mail address and password | 0% | Thu 19-07-18 | Mon 23-07-18 | 36 | BA
GUI-User Management-Password initialization function | 0% | Mon 23-07-18 | Tue 24-07-18 | 98 | BA
GUI-User Management-Self update for OEM user | 0% | Tue 24-07-18 | Thu 26-07-18 | 99 | BA
GUI-User Management-OEM user CRUDS for Admin user | 0% | Thu 26-07-18 | Fri 27-07-18 | 100 | BA
GUI-User Management-Admin user CRUDS for Admin user | 0% | Fri 27-07-18 | Mon 30-07-18 | 101 | BA
Requirement specification document preparation | 0% | Mon 30-07-18 | Fri 03-08-18 | 102 | BA
High level design document preparation | 0% | Fri 03-08-18 | Mon 06-08-18 | 103 | BA
Development | 0% | Fri 03-08-18 | Mon 20-08-18
Coding & Unit Testing | 0% | Fri 03-08-18 | Thu 16-08-18
GUI-User Management-Authenticate using mail address and password | 0% | Fri 03-08-18 | Thu 09-08-18 | 32 | Developer 1
GUI-User Management-Password initialization function | 0% | Thu 09-08-18 | Mon 13-08-18 | 107 | Developer 1
GUI-User Management-Self update for OEM user | 0% | Fri 03-08-18 | Wed 08-08-18 | 32 | Developers 2
GUI-User Management-OEM user CRUDS for Admin user | 0% | Wed 08-08-18 | Mon 13-08-18 | 109 | Developers 2
GUI-User Management-Admin user CRUDS for Admin user | 0% | Mon 13-08-18 | Thu 16-08-18 | 108 | Developer 1
Code Review | 0% | Thu 16-08-18 | Mon 20-08-18
Code review and improvements | 0% | Thu 16-08-18 | Mon 20-08-18 | 111 | Developer 1,Developers 2
SIT Testing | 0% | Wed 08-08-18 | Mon 20-08-18
GUI-User Management-Authenticate using mail address and password | 0% | Thu 09-08-18 | Mon 13-08-18 | 107 | QA 1
GUI-User Management-Password initialization function | 0% | Mon 13-08-18 | Tue 14-08-18 | 108 | QA 1
GUI-User Management-Self update for OEM user | 0% | Wed 08-08-18 | Thu 09-08-18 | 109 | QA2
GUI-User Management-OEM user CRUDS for Admin user | 0% | Mon 13-08-18 | Tue 14-08-18 | 110 | QA2
GUI-User Management-Admin user CRUDS for Admin user | 0% | Thu 16-08-18 | Mon 20-08-18 | 111 | QA 1
Peer Review | 0% | Mon 13-08-18 | Mon 20-08-18
Peer Review & Improvements | 0% | Mon 13-08-18 | Mon 20-08-18 |  | PM
Sprint #4 - UAT | 0% | Mon 20-08-18 | Mon 27-08-18
UAT Testing and Feedback | 0% | Mon 20-08-18 | Mon 27-08-18 | 119 | Client
Sprint #5 (Dev, UT, SIT) | 0% | Mon 20-08-18 | Fri 31-08-18
Requirement Clarification & Documentation | 0% | Mon 06-08-18 | Mon 20-08-18
GUI-User Management-ISP CRUD Operation | 0% | Mon 06-08-18 | Wed 08-08-18 | 104 | BA
GUI-User Management-GIP Operations | 0% | Wed 08-08-18 | Thu 09-08-18 | 126 | BA
GUI-User Management-File information (View count, Final view date, uploaded by) | 0% | Thu 09-08-18 | Fri 10-08-18 | 127 | BA
GUI-User Management-Application Configurations/Settings | 0% | Fri 10-08-18 | Mon 13-08-18 | 128 | BA
Requirement specification document preparation | 0% | Mon 13-08-18 | Wed 15-08-18 | 129 | BA
High level design document preparation | 0% | Wed 15-08-18 | Mon 20-08-18 | 130 | BA
Development | 0% | Mon 20-08-18 | Thu 30-08-18
Coding & Unit Testing | 0% | Mon 20-08-18 | Tue 28-08-18
GUI-User Management-ISP CRUD Operation | 0% | Mon 20-08-18 | Thu 23-08-18 | 96 | Developers 2
GUI-User Management-GIP Operations | 0% | Mon 20-08-18 | Thu 23-08-18 | 96 | Developer 1
GUI-User Management-File information (View count, Final view date, uploaded by) | 0% | Thu 23-08-18 | Tue 28-08-18 | 134 | Developers 2
GUI-User Management-Application Configurations/Settings | 0% | Thu 23-08-18 | Tue 28-08-18 | 135 | Developer 1
Code Review | 0% | Tue 28-08-18 | Thu 30-08-18
Code review and improvements | 0% | Tue 28-08-18 | Thu 30-08-18 | 137 | Developers 2,Developer 1
SIT Testing | 0% | Thu 23-08-18 | Fri 31-08-18
GUI-User Management-ISP CRUD Operation | 0% | Thu 23-08-18 | Tue 28-08-18 | 134 | QA2
GUI-User Management-GIP Operations | 0% | Thu 23-08-18 | Tue 28-08-18 | 135 | QA 1
GUI-User Management-File information (View count, Final view date, uploaded by) | 0% | Tue 28-08-18 | Fri 31-08-18 | 136 | QA2
GUI-User Management-Application Configurations/Settings | 0% | Tue 28-08-18 | Thu 30-08-18 | 137 | QA 1
Peer Review | 0% | Fri 24-08-18 | Fri 31-08-18
Peer Review & Improvements | 0% | Fri 24-08-18 | Fri 31-08-18 |  | PM
Sprint #5 - UAT | 0% | Fri 31-08-18 | Fri 07-09-18
UAT Testing and Feedback | 0% | Fri 31-08-18 | Fri 07-09-18 | 146 | Client
Sprint #6 (Dev, UT, SIT) | 0% | Fri 31-08-18 | Fri 14-09-18 | 96
Requirement Clarification & Documentation | 0% | Mon 20-08-18 | Mon 03-09-18
GUI-File Download-Month wise file list search | 0% | Mon 20-08-18 | Wed 22-08-18 | 131 | BA
GUI-File Download-Download selected files | 0% | Wed 22-08-18 | Thu 23-08-18 | 151 | BA
GUI-File upload-File upload related to OEM user | 0% | Thu 23-08-18 | Fri 24-08-18 | 152 | BA
GUI-File upload-Upload cancellation | 0% | Fri 24-08-18 | Mon 27-08-18 | 153 | BA
Requirement specification document preparation | 0% | Mon 27-08-18 | Wed 29-08-18 | 154 | BA
High level design document preparation | 0% | Wed 29-08-18 | Mon 03-09-18 | 155 | BA
Development | 0% | Fri 31-08-18 | Fri 14-09-18 | 124
Coding & Unit Testing | 0% | Fri 31-08-18 | Fri 14-09-18
GUI-File Download-Month wise file list search | 0% | Fri 31-08-18 | Fri 07-09-18 | 124 | Developer 1
GUI-File Download-Download selected files | 0% | Fri 07-09-18 | Fri 14-09-18 | 159 | Developer 1
GUI-File upload-File upload related to OEM user | 0% | Fri 31-08-18 | Fri 07-09-18 | 124 | Developers 2
GUI-File upload-Upload cancellation | 0% | Fri 07-09-18 | Tue 11-09-18 | 161 | Developers 2
Code Review | 0% | Tue 11-09-18 | Thu 13-09-18
Code review and improvements | 0% | Tue 11-09-18 | Thu 13-09-18 | 162 | Developer 1,Developers 2
SIT Testing | 0% | Fri 07-09-18 | Fri 14-09-18
GUI-File Download-Month wise file list search | 0% | Fri 07-09-18 | Wed 12-09-18 | 159 | QA 1
GUI-File Download-Download selected files | 0% | Wed 12-09-18 | Fri 14-09-18 | 166 | QA 1
GUI-File upload-File upload related to OEM user | 0% | Fri 07-09-18 | Wed 12-09-18 | 161 | QA2
GUI-File upload-Upload cancellation | 0% | Wed 12-09-18 | Fri 14-09-18 | 168 | QA2
Peer Review | 0% | Thu 06-09-18 | Fri 14-09-18
Peer Review & Improvements | 0% | Thu 06-09-18 | Fri 14-09-18 |  | PM
Sprint #6 - UAT | 0% | Fri 14-09-18 | Fri 21-09-18
UAT Testing and Feedback | 0% | Fri 14-09-18 | Fri 21-09-18 | 171 | Client
Sprint #7 (Dev, UT, SIT) | 0% | Mon 17-09-18 | Mon 01-10-18
Requirement Clarification & Documentation | 0% | Mon 03-09-18 | Wed 19-09-18
GUI-Notification-Automatic mail notification function after certain period of time once the upload was completed. | 0% | Mon 03-09-18 | Thu 06-09-18 | 156 | BA
GUI-Notification-Automatic notification on/off selection | 0% | Thu 06-09-18 | Mon 10-09-18 | 176 | BA
GUI-Notification-Cancel transmission while cancelling upload | 0% | Mon 10-09-18 | Wed 12-09-18 | 177 | BA
Requirement specification document preparation | 0% | Wed 12-09-18 | Fri 14-09-18 | 178 | BA
High level design document preparation | 0% | Fri 14-09-18 | Wed 19-09-18 | 179 | BA
Development | 0% | Fri 14-09-18 | Thu 27-09-18
Coding & Unit Testing | 0% | Fri 14-09-18 | Mon 24-09-18
GUI-Notification-Automatic mail notification function after certain period of time once the upload was completed. | 0% | Fri 14-09-18 | Mon 24-09-18 | 149 | Developer 1
GUI-Notification-Automatic notification on/off selection | 0% | Fri 14-09-18 | Thu 20-09-18 | 149 | Developers 2
GUI-Notification-Cancel transmission while cancelling upload | 0% | Thu 20-09-18 | Mon 24-09-18 | 184 | Developers 2
Code Review | 0% | Mon 24-09-18 | Thu 27-09-18
Code review and improvements | 0% | Mon 24-09-18 | Thu 27-09-18 | 185 | Developer 1,Developers 2
SIT Testing | 0% | Thu 20-09-18 | Mon 01-10-18
GUI-Notification-Automatic mail notification function after certain period of time once the upload was completed. | 0% | Mon 24-09-18 | Mon 01-10-18 | 183 | QA 1
GUI-Notification-Automatic notification on/off selection | 0% | Thu 20-09-18 | Tue 25-09-18 | 184 | QA2
GUI-Notification-Cancel transmission while cancelling upload | 0% | Tue 25-09-18 | Thu 27-09-18 | 190 | QA2
Peer Review | 0% | Fri 21-09-18 | Mon 01-10-18
Peer Review & Improvements | 0% | Fri 21-09-18 | Mon 01-10-18 |  | PM
Sprint #7 - UAT | 0% | Mon 01-10-18 | Mon 08-10-18
UAT Testing and Feedback | 0% | Mon 01-10-18 | Mon 08-10-18 | 193 | Client
User Manual Preparation & Review | 0% | Wed 19-09-18 | Wed 10-10-18
User Manual Preparation | 0% | Wed 19-09-18 | Mon 01-10-18 | 180 | BA
User Manual Review | 0% | Tue 25-09-18 | Mon 01-10-18 |  | PM
User Manual Translation (English to Japanese) | 0% | Mon 01-10-18 | Wed 10-10-18 | 198 | Bilingual
Final project Activities | 0% | Tue 18-09-18 | Thu 11-10-18 | 174
Deployement procedure creation | 0% | Mon 01-10-18 | Wed 03-10-18 | 174 | Developer 1
Deployement procedure review | 0% | Wed 03-10-18 | Thu 04-10-18 | 201 | BA
Regression Testing | 0% | Mon 01-10-18 | Tue 09-10-18 | 174 | QA 1
Performance Testing | 0% | Mon 01-10-18 | Wed 03-10-18 | 174 | QA2
Security Testing | 0% | Wed 03-10-18 | Fri 05-10-18 | 204 | QA2
Test delivarables preparation | 0% | Tue 09-10-18 | Thu 11-10-18 | 203 | QA 1,QA2
Sharing the delivarables and Signoff | 0% | Thu 11-10-18 | Fri 12-10-18
Sharing the delivarables and Signoff | 0% | Thu 11-10-18 | Fri 12-10-18 | 200 | PM

## Project Risk
# | Project Risk | Mitigation plan | Remarks